## Sprint1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 10.11.2021, 17:30
Group Number |  | 26
Participant 1 |  | if19b136
Participant 2 |  | if20b066
Participant 3 |  | if19b043
Participant 4 |  | if19b124
Participant 5 |  | if20b256
Mentor |  | Petz Markus
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | read documentation | 40 | 43.5 | 3.5 |  | 1
2 | install lakka on rpi4 + config | 16 | 14 | -2 | 1
3 | online research on how to setup lakka | 10 | 10 | 0 | 1 |  | only 1 piece of hardware so far
4 | setup rpi4 | 25 | 32 | 7
5 | evaluate difference lakka and retropie | 20 | 23 | 3
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 11.5 | 2 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint2
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 24.11.2021, 19:00
Group Number |  | 26
Participant 1 |  | if19b136
Participant 2 |  | if20b066
Participant 3 |  | if19b043
Participant 4 |  | if19b124
Participant 5 |  | if20b256
Mentor |  | Petz Markus
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | install & setup emulator | 10 | 10 | 0 | 1
2 | set up development api | 10 | 0 | -10 |  | 1
3 | first implementations | 15 | 0 | -15 |  | 1 | no coding so far, due to time issues
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -25 | 1 | 2
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint3
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 08.12.2021, 18:00
Group Number |  | 26
Participant 1 |  | if19b136
Participant 2 |  | if20b066
Participant 3 |  | if19b043
Participant 4 |  | if19b124
Participant 5 |  | if20b256
Mentor |  | Petz Markus
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | look into skeletor | 10 | 10 | 0 | 1
2 | look into cmake | 10 | 10 | 0 | 1
3 | load core into retroarch | 100 | 20 | -80 |  | 1 | could not build libretro core
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -80 | 2 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint4
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 15.12.2021, 18:30
Group Number |  | 26
Participant 1 |  | if19b136
Participant 2 |  | if20b066
Participant 3 |  | if19b043
Participant 4 |  | if19b124
Participant 5 |  | if20b256
Mentor |  | Petz Markus
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | look into skeletor | 10 | 10 | 0 | 1
2 | look into cmake | 10 | 10 | 0 | 1
3 | load core into retroarch | 100 | 40 | -60 |  | 1 | can compile and create .dll, some methods still missing
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -60 | 2 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint5
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 12.01.2021, 16:00
Group Number |  | 26
Participant 1 |  | if19b136
Participant 2 |  | if20b066
Participant 3 |  | if19b043
Participant 4 |  | if19b124
Participant 5 |  | if20b256
Mentor |  | Petz Markus
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | 1 | failed | remarks
1 | load core into retroarch | 15 | 10 | -5 | 1
2 | debug messages in console | 5 | 3 | -2 | 1
3 | IO im core run | 20 | 6 | -14 | 1
4 | output various geometric shapes | 15 | 10 | -5 | 1 |  | circle, square, triangle
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -26 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol